MSc Project Timeline 2026 - Merritt

| Week / Date | Project plans/milestones | Uta - Comments |
| --- | --- | --- |
| Week 1 / June 1 | - Read ethics application and supporting documents - Complete data protection training and data protection for research on Learn Ultra - Unpack the data, get the PostGreSQL database going - Think about how to get the order of locations extracted from the original works - Start sketching visualization ideas (on Miro? Figma? Sketchbook physical?) - Start Overleaf project for your dissertation (see example dissertation posted in your Teams folder as a template). | Supervision meetings on request – Monday & Tuesday Uta to send Merritt detailed feedback on IPP |
| Week 2 / June 8 |  |  |
| Week 3 / June 15 | - Unpack the data, get the PostGreSQL database going - Think about user-centred feedback sessions: - Who are you going to recruit (who is the audience of your sketches)? - How will the feedback session take place (in-person, or online) - What do you want to know from potential audiences? - How will you introduce your sketches/prototypes? - Prepare the study forms – modify for your study. - Plan here in the timeline when you want to run the study. - Fingerprint sketches in progress – refine? - Reader-plot - Reader-sketch? - Network sketch - What are you hope to achieve with the designs? - Distinguishing between different authors |  |
| Week 4 / June 22 | - Unpack the data, get the PostGreSQL database going - Integrate order of location mentions into the database - Refine sketches/plot ideas – hook them up to real-data - Explore d3.js - Think about the nature of visualizations in R: will they be interactive, will they be static? - Refine designs - Share slides - Share overleaf with me |  |
| Week 5 / June 29 | - Discuss dissertation structure |  |
| Week 6 / July 6 | July 10 – mid-term progress report due | Online supervision meetings |
| Week 7 / July 13 |  | No supervision meetings |
| Week 8 / July 20 |  | No supervision meetings |
| Week 9 / July 27 | - Feedback session |  |
| Week 10 / Aug 3 | - Feedback session |  |
| Week 11 / Aug 10 |  |  |
| Week 12 / Aug 17 |  |  |
| August 21 | Dissertation submission deadline |  |